## Sheet1
ID | Main task | Subtasks | Team | Deadline | Status | Status | Team
1 | Contact two teams for peer-review |  | Communication and marketing (Sofiia and Mukhammad) | 12.11.2019 | Done
2 | Require all teams to provide their backlog |  | Communication and marketing (Sofiia and Mukhammad) | 14.11.2019 | Done | Planned | Software (Vladislavs and Jēkabs)
3 | Analyze our MVP and main functionality |  | Communication and marketing (Sofiia and Mukhammad) | 18.11.2019 | Planned | Active | Design (Edvards and Reinis)
4 | Prepare questions for municipality members about the website’s functionality to get feedback |  | Communication and marketing (Sofiia and Mukhammad) | 18.11.2019 | Active | Done | Communication and marketing (Sofiia and Mukhammad)
5 | Prepare questions for Bauska’s citizens about the website’s functionality |  | Communication and marketing (Sofiia and Mukhammad) | 18.11.2019 | Planned |  | Project Management and strategy (Zahid and Benoit)
6 | Get feedback from the municipality, specifically, Ilze Tijone, referring to our website’s functionality. |  | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
7 |  | Request additional municipality workers to analyze our website | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
8 |  | Record feedback marking strong and weak points | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
9 |  | Record information about suggested improvements | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
10 |  | Analyze feedback and provide a structured report for IT team | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
11 |  | Organize a meeting with IT team to discuss changes required by the municipality members | Communication and marketing (Sofiia and Mukhammad) | 21.11.2019 | Planned
12 | Get feedback from the municipality, specifically, Ilze Tijone, referring to the design of our website. |  | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
13 |  | Request additional municipality workers to analyze the design of our website | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
14 |  | Record feedback marking strong and weak points | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
15 |  | Record information about suggested improvements | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
16 |  | Analyze feedback and provide a structured report for the Designer team | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
17 |  | Organize a meeting with the Designer team to discuss changes required by the municipality members | Communication and marketing (Sofiia and Mukhammad) | 21.11.2019 | Planned
18 | Read the book ‘Essential Scrum’ |  | Communication and marketing (Sofiia and Mukhammad) | 14.11.2019 | Done
19 | Create a presentation according to the book ‘Essential Scrum’, 5 slides about organizing the teamwork, which can help to develop our skills during the project. |  | Communication and marketing (Sofiia and Mukhammad) | 14.11.2019 | Done
20 | Contact with Ilze Tijone to verify improvements. |  | Communication and marketing (Sofiia and Mukhammad) | 27.11.2019 | Planned
21 |  | Provide Ilze with the second version of designs and functionality if changes were made | Communication and marketing (Sofiia and Mukhammad) | 27.11.2019 | Planned
22 |  | Record feedback marking strong and weak points | Communication and marketing (Sofiia and Mukhammad) | 27.11.2019 | Planned
23 |  | Record information about suggested improvements | Communication and marketing (Sofiia and Mukhammad) | 27.11.2019 | Planned
24 |  | Analyze feedback and provide a structured report for IT and Designer teams | Communication and marketing (Sofiia and Mukhammad) | 27.11.2019 | Planned
25 |  | Organize a meeting with IT and Designer team to discuss final changes required by the municipality members | Communication and marketing (Sofiia and Mukhammad) | 28.11.2019 | Planned
26 | Organize a meeting where our team will discuss all scrum ‘technics’ which can help our work and project |  | Communication and marketing (Sofiia and Mukhammad) | 19.11.2019 | Planned
27 | Approach citizens through social media asking for their opinion about our website |  | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
28 |  | Interview approximately 5-15 people | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
29 |  | Analyze feedback and provide a structured report to the whole team | Communication and marketing (Sofiia and Mukhammad) | 21.11.2019 | Planned
30 | Gather necessary information for final presentation |  | Communication and marketing (Sofiia and Mukhammad) | 6.12.2019 | Planned
31 | Develope the base of the design |  | Design (Edvards and Reinis) | 18.11.2019 | Active
32 |  | Find the main color scheme | Design (Edvards and Reinis) | 18.11.2019 | Active
33 |  | Discuss possible color schemes with the team | Design (Edvards and Reinis) | 18.11.2019 | Planned
34 |  | Check what color scheme does the current website use | Design (Edvards and Reinis) | 16.11.2019 | Active
35 |  | Research the existing color schemes for UI | Design (Edvards and Reinis) | 16.11.2019 | Active
36 | Choose the corresponding font |  | Design (Edvards and Reinis) | 16.11.2019 | Planned
37 | Develop logotype |  | Design (Edvards and Reinis) | 16.11.2019 | Active
38 |  | Design several prototypes for the logotype | Design (Edvards and Reinis) | 16.11.2019 | Active
39 | Make a design for the main project page |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
40 |  | Make a design for a filter and sorting sections on the page | Design (Edvards and Reinis) | 18.11.2019 | Planned
41 |  | Make a design for a project table | Design (Edvards and Reinis) | 18.11.2019 | Planned
42 | Develop design for a single project-view page |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
43 |  | Make a design for readable project’s information | Design (Edvards and Reinis) | 18.11.2019 | Planned
44 |  | Design dropdown menu | Design (Edvards and Reinis) | 18.11.2019 | Planned
45 | Develop design for the single project statistics page |  | Design (Edvards and Reinis) | 21.11.2019 | Planned
46 |  | Make a design for displaying charts | Design (Edvards and Reinis) | 21.11.2019 | Planned
47 |  | Make a design for displaying a horizontal progress bar | Design (Edvards and Reinis) | 21.11.2019 | Planned
48 |  | Design dropdown menu | Design (Edvards and Reinis) | 21.11.2019 | Planned
49 |  | Design update log section | Design (Edvards and Reinis) | 21.11.2019 | Planned
50 | Develop design for overall statistics page |  | Design (Edvards and Reinis) | 21.11.2019 | Planned
51 |  | Make a design for displaying charts | Design (Edvards and Reinis) | 21.11.2019 | Planned
52 |  | Make a design for displaying horizontal bar charts | Design (Edvards and Reinis) | 21.11.2019 | Planned
53 |  | Design dropdown menu | Design (Edvards and Reinis) | 21.11.2019 | Planned
54 | Develop design for main page - admin view |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
55 |  | Design of the page, keeping it consistent with user pages | Design (Edvards and Reinis) | 18.11.2019 | Planned
56 |  | Design objects that are unique for admin view | Design (Edvards and Reinis) | 18.11.2019 | Planned
57 | Develop design for a specific project’s page - admin view |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
58 |  | Design of the page, keeping it consistent with user pages | Design (Edvards and Reinis) | 18.11.2019 | Planned
59 |  | Design objects that are unique for admin view | Design (Edvards and Reinis) | 18.11.2019 | Planned
60 | Develop design for a settings page |  | Design (Edvards and Reinis) | 23.11.2019 | Planned
61 |  | Make a design for financer and section lists | Design (Edvards and Reinis) | 23.11.2019 | Planned
62 |  | Make a design of adding options | Design (Edvards and Reinis) | 23.11.2019 | Planned
63 | Confirm the compatibility of the design with the IT team |  | Design (Edvards and Reinis) | 19.11.2019 | Planned
64 | Get feedback on designs from the whole team |  | Design (Edvards and Reinis) | 19.11.2019 | Planned
65 | Get feedback from the Communication team about the municipality’s judgment of website and logotype |  | Design (Edvards and Reinis) | 21.11.2019 | Planned
66 | Make adjustments for the website and logotype |  | Design (Edvards and Reinis) | 24.11.2019 | Planned
67 | Verify the final design |  | Design (Edvards and Reinis) | 27.11.2019 | Planned
68 | Make the final adjustments |  | Design (Edvards and Reinis) | 4.12.2019 | Planned
69 | Develop a presentation about Iteration 1 |  | Design (Edvards and Reinis) | 21.11.2019 | Planned
70 |  | Get feedback from the whole team | Design (Edvards and Reinis) | 21.11.2019 | Planned
71 |  | Make the adjustments if necessary | Design (Edvards and Reinis) | 21.11.2019 | Planned
72 | Develop presentation about Iteration 2 |  | Design (Edvards and Reinis) | 28.11.2019 | Planned
73 |  | Get feedback from the whole team | Design (Edvards and Reinis) | 28.11.2019 | Planned
74 |  | Make the adjustments if necessary | Design (Edvards and Reinis) | 28.11.2019 | Planned
75 | Develope presentation for Final pitch |  | Design (Edvards and Reinis) | 7.12.2019 | Planned
76 |  | Get feedback from the whole team | Design (Edvards and Reinis) | 7.12.2019 | Planned
77 |  | Make the adjustments if necessary | Design (Edvards and Reinis) | 8.12.2019 | Planned
78 | Help Communication team to contact Bauska municipality to get feedback |  | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Active
79 |  | Plan and verify times | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Active
80 |  | Work with Communication team to help to organize a meeting with municipality members and possibly Bauska’s citizens | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
81 | Get feedback from the IT team about the status of their MVP |  | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Planned
82 | Get feedback from the Designer team about the status of the design of our website |  | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Planned
83 | Update Backlog if necessary |  | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
84 | Help Communication team to organize and run a meeting about “Scrum” practices |  | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Active
85 | Plan meeting for the whole team to discuss and improve the functionality of our website |  | Project Management and strategy (Zahid and Benoit) | 22.11.2019 | Planned
86 | Plan a meeting for the whole team to discuss and improve the design of our website |  | Project Management and strategy (Zahid and Benoit) | 22.11.2019 | Planned
87 | Organize a meeting for the whole team to discuss feedback from the municipality and citizens, and develop a further plan |  | Project Management and strategy (Zahid and Benoit) | 21.11.2019 | Planned
88 | Update Backlog if required |  | Project Management and strategy (Zahid and Benoit) | 22.11.2019 | Planned
89 | Make a plan for the presentation about Iteration 1 |  | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
90 |  | Get feedback from the team and improve the plan | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
91 | Get feedback from the IT team about the updated version of the website |  | Project Management and strategy (Zahid and Benoit) | 24.11.2019 | Planned
92 | Get feedback from the Designer team about the updated version of the website |  | Project Management and strategy (Zahid and Benoit) | 24.11.2019 | Planned
93 | Organize a meeting for the whole team to discuss final feedback from the municipality and citizens, and develop a further plan |  | Project Management and strategy (Zahid and Benoit) | 25.11.2019 | Planned
94 | Get feedback from the IT team about the updated version of the website |  | Project Management and strategy (Zahid and Benoit) | 27.11.2019 | Planned
95 | Get feedback from the Designer team about the updated version of the website |  | Project Management and strategy (Zahid and Benoit) | 27.11.2019 | Planned
96 | Make a plan for the presentation about Iteration 2 |  | Project Management and strategy (Zahid and Benoit) | 27.11.2019 | Planned
97 |  | Get feedback from the teams and improve the plan | Project Management and strategy (Zahid and Benoit) | 27.11.2019 | Planned
98 | Make a plan for the Final presentation |  | Project Management and strategy (Zahid and Benoit) | 3.12.2019 | Planned
99 |  | Get feedback from the teams and improve the plan | Project Management and strategy (Zahid and Benoit) | 4.12.2019 | Planned
100 | Get feedback from the Designer team about final presentation’s template |  | Project Management and strategy (Zahid and Benoit) | 7.12.2019 | Planned
101 | Get feedback from the IT team about the website’s status and accessibility |  | Project Management and strategy (Zahid and Benoit) | 7.12.2019 | Planned
102 | Ensure our team is aware of specifications for the final presentation |  | Project Management and strategy (Zahid and Benoit) | 7.12.2019 | Planned
103 | Ensure each team is prepared for the final presentation |  | Project Management and strategy (Zahid and Benoit) | 9.12.2019 | Planned
104 | Develop the main project page |  | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
105 |  | Add output with a list of all projects from the database, where each project includes the project name, project status, and time of implementation | Software (Vladislavs and Jēkabs) | 13.11.2019 | Done
106 |  | Add possibility to search by keyword in the name | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
107 |  | Add possibility to filter by status | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
108 |  | Add possibility to filter by the financier | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
109 |  | Add possibility to sort by status | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
110 |  | Add possibility to sort by budget | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
111 |  | Add a button that links to the overall statistics page | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
112 |  | Test functionality of the main project page | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
113 | Develop one specific project’s output page |  | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
114 |  | Include all information from the database | Software (Vladislavs and Jēkabs) | 14.11.2019 | Done
115 |  | Add drop-down menu with two options “Status” and “About”(default) | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
116 |  | Test functionality of the project’s output page | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
117 | Develop one specific project’s status page |  | Software (Vladislavs and Jēkabs) | 16.11.2019 | Active
118 |  | Research the Net on many-to-many relation databases topic | Software (Vladislavs and Jēkabs) | 13.11.2019 | Done
119 |  | Research the Net for the solution of visual data representation | Software (Vladislavs and Jēkabs) | 13.11.2019 | Done
120 |  | Add project completion horizontal progress bar | Software (Vladislavs and Jēkabs) | 13.11.2019 | Done
121 |  | Add update log with dates and short descriptions of update | Software (Vladislavs and Jēkabs) | 14.11.2019 | Done
122 |  | Add visual data representation object (pie chart) which represents a comparison of budget spent with the project’s budget | Software (Vladislavs and Jēkabs) | 16.11.2019 | Active
123 |  | Add visual data representation object (pie chart) which represents a comparison of budget spent with all projects’ budget | Software (Vladislavs and Jēkabs) | 16.11.2019 | Active
124 |  | Test functionality of the specific project’s status page | Software (Vladislavs and Jēkabs) | 16.11.2019 | Active
125 | Develop Bauska’s overall project statistics page |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
126 |  | Add visual data representation object (horizontal bar charts) with financing sources (Number of projects financed by the financier) | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
127 |  | Add visual data representation object (horizontal bar charts) with the representation of the amount of money financed by financier | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
128 |  | Add dropdown menu with an option to choose a different year of statistics | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
129 |  | Test functionality of Bauska’s overall project statistics page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
130 | Develop admin login page |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
131 |  | Develop the possibility to log in for pre-defined users (limited amount) | Software (Vladislavs and Jēkabs) | 18.11.2019 | Done
132 |  | Secure admin view by redirecting to the admin page if the user tries to directly change the URL to access admin view | Software (Vladislavs and Jēkabs) | 18.11.2019 | Done
133 |  | Test functionality and security of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
134 | Develop Main Page for Admin |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
135 |  | Add the same main project page the regular user has | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
136 |  | Add possibility to log out (back to the login page) | Software (Vladislavs and Jēkabs) | 18.11.2019 | Done
137 |  | Add button to create a new project | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
138 |  | Add button to go to the single project editing page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
139 |  | Add button for the settings page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
140 |  | Test functionality of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
141 | Develop "New project" page |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
142 |  | Add possibility for the admin to create a new project by entering information in pre-defined fields | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
143 |  | Add possibility to write logs in “Update log” section | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
144 |  | Add the possibility to save a new project | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
145 |  | Test functionality of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
146 | Existing project page |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
147 |  | Add possibility for the admin to edit project’s information by changing it in pre-defined fields with existing information | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
148 |  | Add the possibility to write logs in “Update log” section | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
149 |  | Add the possibility to save changes | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
150 |  | Add the possibility to delete the whole project | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
151 |  | Test functionality of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
152 | Settings page |  | Software (Vladislavs and Jēkabs) | 26.11.2019 | Planned
153 |  | Add output of all possible financers | Software (Vladislavs and Jēkabs) | 26.11.2019 | Planned
154 |  | Add possibility to delete existing financier from the filter | Software (Vladislavs and Jēkabs) | 26.11.2019 | Planned
155 |  | Add the possibility to add new financier to the filter | Software (Vladislavs and Jēkabs) | 26.11.2019 | Planned
156 |  | Test functionality of the page | Software (Vladislavs and Jēkabs) | 26.11.2019 | Planned
157 | Discuss design |  | Software (Vladislavs and Jēkabs) | 21.11.2019 | Planned
158 |  | Discuss design with Designer team | Software (Vladislavs and Jēkabs) | 21.11.2019 | Planned
159 |  | Review design | Software (Vladislavs and Jēkabs) | 21.11.2019 | Planned
160 |  | Make changes in the design if required | Software (Vladislavs and Jēkabs) | 23.11.2019 | Planned
161 |  | Approve new design if were made | Software (Vladislavs and Jēkabs) | 24.11.2019 | Planned
162 |  | Adapt the main project page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
163 |  | Adapt one specific project’s output page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
164 |  | Adapt one specific project’s status page to developed design | Software (Vladislavs and Jēkabs) | 21.11.2019 | Planned
165 |  | Adapt Bauska’s overall project statistics page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
166 |  | Adapt admin Login page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
167 |  | Adapt admin Main Page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
168 |  | Adapt “New project page” to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
169 |  | Adapt “Existing project page” to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
170 |  | Adapt “Settings page” to developed design | Software (Vladislavs and Jēkabs) | 24.11.2019 | Planned
171 | Get feedback |  | Software (Vladislavs and Jēkabs) | 24.11.2019 | Planned
172 |  | Adapt or change our webpage according to a summary from the Communication team | Software (Vladislavs and Jēkabs) | 24.11.2019 | Planned
173 |  | Verify new version | Software (Vladislavs and Jēkabs) | 25.11.2019 | Planned
174 |  | Make last adjustments of the website | Software (Vladislavs and Jēkabs) | 30.11.2019 | Planned
175 | Export website to the working domain and hosting |  | Software (Vladislavs and Jēkabs) | 6.12.2019 | Planned
176 |  | Test all functionality | Software (Vladislavs and Jēkabs) | 8.12.2019 | Planned