## Sheet1
ID (From Backlog) | Main task | Subtasks | Team | Deadline | Status | Summary
1 | Contact two teams for peer-review |  | Communication and marketing (Sofiia and Mukhammad) | 12.11.2019 | Done | The main goal of the first iteration is to develop MVP and receive feedback from Bauska's municipality and, possibly, citizens. All teams are going to cooperate in order to achieve the best possible quality of the first iteration results. Teams are going to develop all the functionality and design of our website. All team members are going to judge the first version of a fully developed website and make required improvements.
2 | Require all teams to provide their backlog |  | Communication and marketing (Sofiia and Mukhammad) | 14.11.2019 | Done
3 | Analyze our MVP and main functionality |  | Communication and marketing (Sofiia and Mukhammad) | 18.11.2019 | Planned
4 | Prepare questions for municipality members about the website’s functionality to get feedback |  | Communication and marketing (Sofiia and Mukhammad) | 18.11.2019 | Active
5 | Prepare questions for Bauska’s citizens about the website’s functionality |  | Communication and marketing (Sofiia and Mukhammad) | 18.11.2019 | Planned
6 | Get feedback from the municipality, specifically, Ilze Tijone, referring to our website’s functionality. |  | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
7 |  | Request additional municipality workers to analyze our website | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
8 |  | Record feedback marking strong and weak points | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
9 |  | Record information about suggested improvements | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
10 |  | Analyze feedback and provide a structured report for IT team | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
11 |  | Organize a meeting with IT team to discuss changes required by the municipality members | Communication and marketing (Sofiia and Mukhammad) | 21.11.2019 | Planned
12 | Get feedback from the municipality, specifically, Ilze Tijone, referring to the design of our website. |  | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
13 |  | Request additional municipality workers to analyze the design of our website | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
14 |  | Record feedback marking strong and weak points | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
15 |  | Record information about suggested improvements | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
16 |  | Analyze feedback and provide a structured report for the Designer team | Communication and marketing (Sofiia and Mukhammad) | 20.11.2019 | Planned
17 |  | Organize a meeting with the Designer team to discuss changes required by the municipality members | Communication and marketing (Sofiia and Mukhammad) | 21.11.2019 | Planned
18 | Read the book ‘Essential Scrum’ |  | Communication and marketing (Sofiia and Mukhammad) | 14.11.2019 | Done
19 | Create a presentation according to the book ‘Essential Scrum’, 5 slides about organizing the teamwork, which can help to develop our skills during the project. |  | Communication and marketing (Sofiia and Mukhammad) | 14.11.2019 | Done
31 | Develope the base of the design |  | Design (Edvards and Reinis) | 18.11.2019 | Active
32 |  | Find the main color scheme | Design (Edvards and Reinis) | 18.11.2019 | Active
33 |  | Discuss possible color schemes with the team | Design (Edvards and Reinis) | 18.11.2019 | Planned
34 |  | Check what color scheme does the current website use | Design (Edvards and Reinis) | 16.11.2019 | Active
35 |  | Research the existing color schemes for UI | Design (Edvards and Reinis) | 16.11.2019 | Active
36 | Choose the corresponding font |  | Design (Edvards and Reinis) | 16.11.2019 | Planned
37 | Develop logotype |  | Design (Edvards and Reinis) | 16.11.2019 | Active
38 |  | Design several prototypes for the logotype | Design (Edvards and Reinis) | 16.11.2019 | Active
39 | Make a design for the main project page |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
40 |  | Make a design for a filter and sorting sections on the page | Design (Edvards and Reinis) | 18.11.2019 | Planned
41 |  | Make a design for a project table | Design (Edvards and Reinis) | 18.11.2019 | Planned
42 | Develop design for a single project-view page |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
43 |  | Make a design for readable project’s information | Design (Edvards and Reinis) | 18.11.2019 | Planned
44 |  | Design dropdown menu | Design (Edvards and Reinis) | 18.11.2019 | Planned
54 | Develop design for main page - admin view |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
55 |  | Design of the page, keeping it consistent with user pages | Design (Edvards and Reinis) | 18.11.2019 | Planned
56 |  | Design objects that are unique for admin view | Design (Edvards and Reinis) | 18.11.2019 | Planned
57 | Develop design for a specific project’s page - admin view |  | Design (Edvards and Reinis) | 18.11.2019 | Planned
58 |  | Design of the page, keeping it consistent with user pages | Design (Edvards and Reinis) | 18.11.2019 | Planned
59 |  | Design objects that are unique for admin view | Design (Edvards and Reinis) | 18.11.2019 | Planned
63 | Confirm the compatibility of the design with the IT team |  | Design (Edvards and Reinis) | 19.11.2019 | Planned
64 | Get feedback on designs from the whole team |  | Design (Edvards and Reinis) | 19.11.2019 | Planned
65 | Get feedback from the Communication team about the municipality’s judgment of website and logotype |  | Design (Edvards and Reinis) | 21.11.2019 | Planned
78 | Help Communication team to contact Bauska municipality to get feedback |  | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Active
79 |  | Plan and verify times | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Active
80 |  | Work with Communication team to help to organize a meeting with municipality members and possibly Bauska’s citizens | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
81 | Get feedback from the IT team about the status of their MVP |  | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Planned
82 | Get feedback from the Designer team about the status of the design of our website |  | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Planned
83 | Update Backlog if necessary |  | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
84 | Help Communication team to organize and run a meeting about “Scrum” practices |  | Project Management and strategy (Zahid and Benoit) | 19.11.2019 | Active
85 | Plan meeting for the whole team to discuss and improve the functionality of our website |  | Project Management and strategy (Zahid and Benoit) | 22.11.2019 | Planned
86 | Plan a meeting for the whole team to discuss and improve the design of our website |  | Project Management and strategy (Zahid and Benoit) | 22.11.2019 | Planned
87 | Organize a meeting for the whole team to discuss feedback from the municipality and citizens, and develop a further plan |  | Project Management and strategy (Zahid and Benoit) | 21.11.2019 | Planned
88 | Update Backlog if required |  | Project Management and strategy (Zahid and Benoit) | 22.11.2019 | Planned
89 | Make a plan for the presentation about Iteration 1 |  | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
90 |  | Get feedback from the team and improve the plan | Project Management and strategy (Zahid and Benoit) | 20.11.2019 | Planned
104 | Develop the main project page |  | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
105 |  | Add output with a list of all projects from the database, where each project includes the project name, project status, and time of implementation | Software (Vladislavs and Jēkabs) | 13.11.2019 | Done
106 |  | Add possibility to search by keyword in the name | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
107 |  | Add possibility to filter by status | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
108 |  | Add possibility to filter by the financier | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
109 |  | Add possibility to sort by status | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
110 |  | Add possibility to sort by budget | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
111 |  | Add a button that links to the overall statistics page | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
112 |  | Test functionality of the main project page | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
113 | Develop one specific project’s output page |  | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
114 |  | Include all information from the database | Software (Vladislavs and Jēkabs) | 14.11.2019 | Done
115 |  | Add drop-down menu with two options “Status” and “About”(default) | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
116 |  | Test functionality of the project’s output page | Software (Vladislavs and Jēkabs) | 15.11.2019 | Done
130 | Develop admin login page |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
131 |  | Develop the possibility to log in for pre-defined users (limited amount) | Software (Vladislavs and Jēkabs) | 18.11.2019 | Done
132 |  | Secure admin view by redirecting to the admin page if the user tries to directly change the URL to access admin view | Software (Vladislavs and Jēkabs) | 18.11.2019 | Done
133 |  | Test functionality and security of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
134 | Develop Main Page for Admin |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
135 |  | Add the same main project page the regular user has | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
136 |  | Add possibility to log out (back to the login page) | Software (Vladislavs and Jēkabs) | 18.11.2019 | Done
137 |  | Add button to create a new project | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
138 |  | Add button to go to the single project editing page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
139 |  | Add button for the settings page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
140 |  | Test functionality of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Active
141 | Develop "New project" page |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
142 |  | Add possibility for the admin to create a new project by entering information in pre-defined fields | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
143 |  | Add possibility to write logs in “Update log” section | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
144 |  | Add the possibility to save a new project | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
145 |  | Test functionality of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
146 | Existing project page |  | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
147 |  | Add possibility for the admin to edit project’s information by changing it in pre-defined fields with existing information | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
148 |  | Add the possibility to write logs in “Update log” section | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
149 |  | Add the possibility to save changes | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
150 |  | Add the possibility to delete the whole project | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
151 |  | Test functionality of the page | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
162 |  | Adapt the main project page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
163 |  | Adapt one specific project’s output page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
166 |  | Adapt admin Login page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
167 |  | Adapt admin Main Page to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
168 |  | Adapt “New project page” to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned
169 |  | Adapt “Existing project page” to developed design | Software (Vladislavs and Jēkabs) | 18.11.2019 | Planned